## Project Plan Spreadsheet Genera
Task ID | Assigned To | Role | Task Name | Description / Action Item | Deliverable | Status
L-01 | Iqbal Gill | Team Lead | Architecture Design | Create full MCP ReAct architecture diagram (Ingestion → VectorDB → Agent → API → GUI). | architecture_diagram.jpg | 🟢 Ready
L-02 | Iqbal Gill | Team Lead | Core Agent Engine | Implement run_manual_agent in backend/agent.py using custom Thought-Action loop. | backend/agent.py | 🟢 Ready
L-03 | Iqbal Gill | Team Lead | Prompt Engineering | Design System Prompt to enforce "Action: Search [...]" protocol & Regex patterns. | Prompt Logic | 🟢 Ready
L-04 | Iqbal Gill | Team Lead | Guardrail Logic | Code is_department_related function to filter non-UET queries. | Guardrail Function | 🟢 Ready
L-05 | Iqbal Gill | Team Lead | Integration | Merge Backend, Frontend, and DB. Perform final system review. | Final GitHub Repo | 🟡 Pending
D-01 | Saliha | Data Engineer | PDF Cleaning | Review UET_Prospectus.pdf and remove noise/headers/footers. | Cleaned PDF | 🟢 Ready
D-02 | Saliha | Data Engineer | Ingestion Script | Write ingest.py using PyPDFLoader & RecursiveCharacterTextSplitter. | backend/ingest.py | 🟢 Ready
D-03 | Saliha | Data Engineer | Vector DB Setup | Configure ChromaDB with nomic-embed-text and run ingestion. | data/vector_db/ | 🟢 Ready
D-04 | Saliha | Data Engineer | Optimization | Set retriever k=2 and limit context chars (Turbo Mode) for speed. | Optimized Config | 🟢 Ready
A-01 | Ayesha | API Dev | Server Setup | Initialize FastAPI app in main.py and configure CORS. | backend/main.py | 🟢 Ready
A-02 | Ayesha | API Dev | Endpoint Creation | Create POST /chat endpoint receiving JSON and returning text. | /chat Endpoint | 🟢 Ready
A-03 | Ayesha | API Dev | Error Handling | Add try-except blocks for 500 errors (LLM timeout/DB fail). | Error Logic | 🟢 Ready
A-04 | Ayesha | API Dev | API Testing | Test API via Postman/cURL to ensure JSON format is correct. | Test Report | 🟡 Pending
F-01 | Faiza | Frontend/QA | GUI Development | Build Streamlit app frontend/app.py with chat history state. | frontend/app.py | 🟢 Ready
F-02 | Faiza | Frontend/QA | API Integration | Connect Streamlit to FastAPI backend using requests library. | Functional UI | 🟢 Ready
F-03 | Faiza | Frontend/QA | Test Suite | Create tests/test_queries.json with 20 Qs (10 Dept, 5 Tricky, 5 Out). | test_queries.json | 🟢 Ready
F-04 | Faiza | Frontend/QA | Video & Demo | Record 6-10 min video showing Arch, Team Plan, and Live Demo. | Video File | 🔴 To Do